## Theo dõi dự án
H3ArT - Artwork Sharing Platform
Title |  | H3ArT - Artwork Sharing Platform |  |  |  |  | Group name | Group 4
LEADER |  | Đặng Công Hưng |  |  |  |  | DATE | 2024-01-01
PROJECT DETAILS | [7 empty] | Layer | Bug
STATUS | PRIORITY | START DATE | END DATE | TASK SECTION | SINGLE TASK | MEMBER | NOTE |  | Bug | Fix
SPRINT 1
Complete | Low | 2024-01-25 | 2024-01-26 | Login | Login | Đặng Công Hưng | 1. Login with system account. | Backend
Complete | Low | 2024-01-25 | 2024-01-26 | Resgister | Register | Đặng Công Hưng | 1. Register an system account. 2. Validates information | Backend
Complete | Low | 2024-01-25 | 2024-01-26 | Homepage | Homepage | Nguyễn Tấn Hưng | Show all artworks. | Both | Purchased artworks appear on the homepage | Nguyễn Tấn Hưng
Complete | Low | 2024-01-25 | 2024-01-26 | Login | Login | Nguyễn Hữu Minh Tài | The login page | FrontEnd
Complete | Low | 2024-01-25 | 2024-01-26 | Register | Register | Phạm Lê Quý Anh | The register page | FrontEnd
SPRINT 2
Complete | Medium | 2024-02-04 | 2024-02-09 | View artworks | Search artworks | Nguyễn Tấn Hưng | Search artwork base on keyword. | Both
Complete | Medium | 2024-02-04 | 2024-02-09 |  | Filter by categories | Nguyễn Tấn Hưng | Filter artwork base on a specific category | Both
Complete | Medium | 2024-02-04 | 2024-02-09 |  | View artwork detail | Nguyễn Tấn Hưng | Go to artwork detail page | Both
Complete | Medium | 2024-02-04 | 2024-02-09 |  | "My order" in the header | Nguyễn Tấn Hưng | "My order" in the header | FrontEnd
Complete | Medium | 2024-02-04 | 2024-02-09 | View artwork detail | Artwork detail | Nguyễn Tấn Hưng | Show detail of the artwork. | Both
Complete | Medium | 2024-02-04 | 2024-02-09 | Login | Login with Facebook | Đặng Công Hưng | 1.Show a Facebook button in the login page. 2. Implement login Facebook | Both
Complete | Medium | 2024-02-04 | 2024-02-09 | Register | Register with Facebook | Đặng Công Hưng | 1.Show a Facebook button in the register page. 2. Implement register Facebook | Both
Complete | High | 2024-02-04 | 2024-02-09 | Cart | Cart Detail | Đặng Công Hưng | 1. Show the name and price of the artwork 2. Show the total price 3. Place order (accept the order) 4. Back to cart | Both
Complete | High | 2024-02-04 | 2024-02-09 | Payment | Pay by Stripe | Đặng Công Hưng | Config Stripe | Both
Complete | Low | 2024-02-04 | 2024-02-09 | View list of artworks | Show the list of artwork | Đặng Công Hưng | Show the (paginatedly) list of artwork (including info) | Both
Complete | Medium | 2024-02-04 | 2024-02-09 | View list of artworks | Search base on keyword | Nguyễn Hữu Minh Tài |  | Both
Complete | Medium | 2024-02-04 | 2024-02-09 |  | CRUD | Nguyễn Hữu Minh Tài | Create, Edit, Deletee artwork | Both
Complete | Low | 2024-02-04 | 2024-02-09 |  | Back to page | Nguyễn Hữu Minh Tài |  | Both
Complete | Low | 2024-02-04 | 2024-02-09 | View list of user accounts | Show the list of user accounts | Nguyễn Hữu Minh Tài | Show the (paginatedly) list of user(including info) | FrontEnd
Complete | Medium | 2024-02-04 | 2024-02-09 |  | Search base on keyword | Nguyễn Hữu Minh Tài |  | Both
Complete | Medium | 2024-02-04 | 2024-02-09 | View artwork detail | Add to cart | Phạm Lê Quý Anh | Add the artwork to cart | Both
Complete | Low | 2024-02-04 | 2024-02-09 |  | Creator profile | Phạm Lê Quý Anh | A link to Creator Profile Page | FrontEnd
Complete | Medium | 2024-02-04 | 2024-02-09 |  | Report artwork | Phạm Lê Quý Anh | Add to Report Artwork List | Both
Complete | Low | 2024-02-04 | 2024-02-09 |  | Back to page | Phạm Lê Quý Anh |  | Both
Complete | Medium | 2024-02-04 | 2024-02-09 |  | More like this section | Phạm Lê Quý Anh | Show 10 random artworks | Both
SPRINT 3
Complete | Medium | 2024-02-19 | 2024-03-02 | View list of user accounts | Search users | Đặng Công Hưng | Search user base on keyword. | Both
Complete | Medium | 2024-02-19 | 2024-03-02 |  | Lock/Unlock users | Đặng Công Hưng | - Lock / Unlock user account - Cannot block admin | Both
Complete | Medium | 2024-02-19 | 2024-03-02 | View list of artworks | Hide report artwork | Đặng Công Hưng |  | Both
Complete | Medium | 2024-02-19 | 2024-03-02 | View list of reported accounts | Lock/Unlock report users | Đặng Công Hưng |  | Both
Complete | Medium | 2024-02-19 | 2024-03-02 | View artwork detail | Like,share,coment artwork | Đặng Công Hưng | using disqus | Both | Cannot SSO
Complete | Medium | 2024-02-19 | 2024-03-02 | View user profile | Edit user profile | Đặng Công Hưng |  | Both
Complete | Low | 2024-02-19 | 2024-03-02 |  | Change password | Đặng Công Hưng |  | Both
Complete | Medium | 2024-02-19 | 2024-03-02 | Login | Login with Google | Nguyễn Hữu Minh Tài | 1.Show a Google button in the login page. 2. Implement login Google | Both
Complete | Medium | 2024-02-19 | 2024-03-02 | Register | Register with Google | Nguyễn Hữu Minh Tài | 1.Show a Google button in the register page. 2. Implement register Google | Both
Complete | High | 2024-02-19 | 2024-03-02 | Login - Email | Verify email | Nguyễn Hữu Minh Tài | Verify email when finishing register | Both
Complete | High | 2024-02-19 | 2024-03-02 |  | Send email | Nguyễn Hữu Minh Tài | Config Send Email | Both
Complete | Medium | 2024-02-19 | 2024-03-02 | View user profile | Change email | Nguyễn Hữu Minh Tài | Verify email when changing | Both
Complete | Medium | 2024-02-19 | 2024-03-02 | View list of packages | Create package | Nguyễn Tấn Hưng | Search user base on keyword. | Both
Complete | Medium | 2024-02-19 | 2024-03-02 |  | Update package | Nguyễn Tấn Hưng | - Lock / Unlock user account - Cannot block admin | Both
Complete | Medium | 2024-02-19 | 2024-03-02 |  | Delete package | Nguyễn Tấn Hưng |  | Both
Complete | Low | 2024-02-19 | 2024-03-02 |  | View list of packages | Nguyễn Tấn Hưng |  | Both
Complete | High | 2024-02-19 | 2024-03-02 | View packages (buy) | View packages | Nguyễn Tấn Hưng | - View packages and choose a package to buy. - Implement buy package | Both
Complete | Low | 2024-02-19 | 2024-03-02 | View user profle | View user profle | Phạm Lê Quý Anh | Showing info of that user | Both
Complete | Medium | 2024-02-19 | 2024-03-02 | View creator | Report creator | Phạm Lê Quý Anh | Add to Report Creator List | Both
Complete | Low | 2024-02-19 | 2024-03-02 | View list of reported creator list | View list of reported creator list | Phạm Lê Quý Anh |  | Both
Complete | Medium | 2024-02-19 | 2024-03-02 | View artwork detail/view bog detail | Creator profile | Phạm Lê Quý Anh |  | Both
SPRINT 4
Complete | Medium | 2024-03-04 | 2024-03-10 | View blogs | View blogs | Đặng Công Hưng | Show all blogs with descending order base on date | Both
Complete | Medium | 2024-03-04 | 2024-03-10 |  | View blog detail | Đặng Công Hưng | Show blog detail | Both
Complete | Medium | 2024-03-04 | 2024-03-10 | View list of blogs | View list of blogs | Đặng Công Hưng | Show list of blogs | Both
Complete | Medium | 2024-03-04 | 2024-03-10 |  | Edit blog | Đặng Công Hưng |  | Both
Complete | Medium | 2024-03-04 | 2024-03-10 |  | Remove blog | Đặng Công Hưng |  | Both
Complete | Medium | 2024-03-04 | 2024-03-10 |  | Create blog | Đặng Công Hưng |  | Both
Complete | High | 2024-03-04 | 2024-03-10 |  | Fix order flow | Đặng Công Hưng |  | Both
Complete | Medium | 2024-03-04 | 2024-03-10 |  | Like,share,comment,report blog | Đặng Công Hưng | using Disqus | Both | Cannot SSO
Complete | Medium | 2024-03-04 | 2024-03-10 | View list of orders | View list of orders | Nguyễn Tấn Hưng | Show list of orders | Both
Complete | Medium | 2024-03-04 | 2024-03-10 |  | View order detail | Nguyễn Tấn Hưng | Show blog detail | Both
Complete | Medium | 2024-03-04 | 2024-03-10 |  | Add order for package | Nguyễn Tấn Hưng |  | Both
Complete | Medium | 2024-03-04 | 2024-03-10 |  | View order detail for pakage | Nguyễn Tấn Hưng |  | Both
Complete | Medium | 2024-03-04 | 2024-03-10 |  | Fix manage users by admin | Nguyễn Tấn Hưng |  | Both
Complete | Medium | 2024-03-04 | 2024-03-10 |  | Fix manage blogs by admin | Nguyễn Tấn Hưng |  | Both
Complete | Medium | 2024-03-04 | 2024-03-10 |  | Fix UI login | Nguyễn Hữu Minh Tài |  | FrontEnd
Complete | Medium | 2024-03-04 | 2024-03-10 |  | Fix UI register | Nguyễn Hữu Minh Tài |  | FrontEnd
Complete | Medium | 2024-03-04 | 2024-03-10 |  | Fix UI layout | Nguyễn Hữu Minh Tài |  | FrontEnd
Complete | Medium | 2024-03-04 | 2024-03-10 | Report blog/ artwork/creator | Add report reason | Nguyễn Hữu Minh Tài |  | Both
Complete | Medium | 2024-03-04 | 2024-03-10 |  | Fix Order Confirmation | Nguyễn Hữu Minh Tài |  | Both
Complete | Medium | 2024-03-04 | 2024-03-10 |  | Send email for order | Nguyễn Hữu Minh Tài |  | Both
Complete | Medium | 2024-03-04 | 2024-03-10 |  | Reset password | Nguyễn Hữu Minh Tài | Verify email | Both
Complete | Medium | 2024-03-04 | 2024-03-10 | View list of blogs | View list of blogs | Phạm Lê Quý Anh | Show list of blogs | Both
Complete | Medium | 2024-03-04 | 2024-03-10 | View blog detail | Report blog | Phạm Lê Quý Anh |  | Both
Complete | Medium | 2024-03-04 | 2024-03-10 |  | Fix UI for access denied | Phạm Lê Quý Anh |  | FrontEnd
Complete | Medium | 2024-03-04 | 2024-03-10 |  | Fix UI for blocked user page | Phạm Lê Quý Anh |  | FrontEnd
Complete | Low | 2024-03-04 | 2024-03-10 |  | Fix admin page | Phạm Lê Quý Anh |  | FrontEnd