## TestReport
Key | Issue Type | Parent | Summary | Status | Assignee | Sprint | Start date | Inferred start date | Due date | Inferred due date | Issue color
NNB-197 | Epic |  | New Account | To Do | Pham Le Quy Anh (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-246 | Story | NNB-197 | TR_NA01_Full Name is required | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-249 | Story | NNB-197 | TR_NA02_Full Name cannot contain numbers. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-250 | Story | NNB-197 | TR_NA03_Email is required. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-252 | Story | NNB-197 | TR_NA04_Email format must be valid. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-253 | Story | NNB-197 | TR_NA05_Password is required. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-254 | Story | NNB-197 | TR_NA06_ Password must be at least 6 and at max 100 characters long. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-256 | Story | NNB-197 | TR_NA07_Password must have at least one non alphanumeric character. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-257 | Story | NNB-197 | TR_NA08_Password must have at least one lowercase character. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-258 | Story | NNB-197 | TR_NA09_ Password must have at least one upper character. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-259 | Story | NNB-197 | TR_NA10_Confirm Password and Password must be the same. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-294 | Story | NNB-197 | TR_NA02_Full Name cannot contain numbers. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-359 | Story | NNB-197 | FV_NA01_Admin can add a new account | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-361 | Story | NNB-197 | FV_NA02_If the full name is null, show an error message. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-363 | Story | NNB-197 | FV_NA03_If the full name contains number, show an error message. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-364 | Story | NNB-197 | FV_NA04_ If the email is null, show an error message. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-365 | Story | NNB-197 | FV_NA05_ If the email is invalid, show an error message. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-366 | Story | NNB-197 | FV_NA06_If the password is null, show an error message. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-371 | Story | NNB-197 | FV_NA10_If the password does not have any upper character, show an error message. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-474 | Story | NNB-197 | TR_NA02_Full Name cannot contain numbers. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-18 | Epic |  | Login | To Do |  |  | 2023-12-23 | 2023-12-23 | 2024-03-31 | 2024-03-31 | purple
NNB-418 | Story | NNB-18 | TR_L01_Email is required. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-420 | Story | NNB-18 | TR_L02_ Email must be valid | Done |  | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-423 | Story | NNB-18 | FV_L01_If the email is null, show an error message. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-426 | Story | NNB-18 | FV_L02_ If the email is not valid, show error message | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-427 | Story | NNB-18 | FV_L03_If the password is null, show error message. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-428 | Story | NNB-18 | FV_L04_If the email does not exist in database, show error message. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-429 | Story | NNB-18 | FV_L05_If the password is not identical to the password in database, show error message. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-430 | Story | NNB-18 | FV_L06_Admin successfully log in to the application. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-431 | Story | NNB-18 | FV_L07_Creator successfully log in to the application. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-432 | Story | NNB-18 | FV_L08_Customer successfully log in to the application. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-433 | Story | NNB-18 | FV_L09_Moderator successfully log in to the application. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-473 | Story | NNB-18 | TR_L28_Email must be valid | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-198 | Epic |  | View List Account | To Do | Nguyen Huu Minh Tai (K17 HCM) |  | 2024-03-14 | 2024-03-14 | 2024-03-31 | 2024-03-31 | purple
NNB-240 | Story | NNB-198 | FV_VLA12_Admin_Admin can view the list of user accounts. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-199 | Epic |  | Update Role | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-409 | Story | NNB-199 | FV_UR013_[Admin]_Admin can update user’s role | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-410 | Story | NNB-199 | FV_UR014_[Admin]_Admin cannot update his role | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-200 | Epic |  | Ban Account | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-242 | Story | NNB-200 | FV_BA27_Admin_Admin can ban user accounts on the Manage User Page. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-243 | Story | NNB-200 | FV_BA28_Admin_Admin cannot ban his own account. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-247 | Story | NNB-200 | FV_BA29_Moderator_Moderator can ban creator accounts on the Report Account List. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-201 | Epic |  | Unban Account | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-248 | Story | NNB-201 | FV_UA30_Admin_Admin can unban a user account on the Manage User Page. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-251 | Story | NNB-201 | FV_UA31_Moderator_Moderator can unban creator accounts on the Report Account List. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-202 | Epic |  | View List package | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-348 | Story | NNB-202 | FV_VLP67_Admin_Admin can view the list of packages. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-203 | Epic |  | Create Package | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-239 | Story | NNB-203 | TR_CP41_Verify Package Name_Package Name is required. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-275 | Story | NNB-203 | FV_CP70_Admin_If the Price of the package is less than 0, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-280 | Story | NNB-203 | TR_CP42_Verify Description_Description is required. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-285 | Story | NNB-203 | TR_CP43_Verify Price_Price must be greater than 0. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-295 | Story | NNB-203 | TR_CP44_Verify Price_Price must be a number. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-303 | Story | NNB-203 | FV_CP71_Admin_If the Amount Post of the package is less than 0, the system will show the error. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-310 | Story | NNB-203 | FV_CP72_Admin_If the Description of the package is blank, the system will show the error. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-315 | Story | NNB-203 | FV_CP73_Admin_If the Package Name is blank, the system will show the error. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-204 | Epic |  | Delete Package | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-297 | Story | NNB-204 | FV_DP76_Admin_Admin should be able to delete the package. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-205 | Epic |  | Update Package | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-316 | Story | NNB-205 | TR_UP45_Verify Package Name_Package Name is required. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-317 | Story | NNB-205 | TR_UP46_Verify Description_Description is required. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-318 | Story | NNB-205 | TR_UP47_Verify Price_Price must greater than 0. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-319 | Story | NNB-205 | TR_UP48_Verify Price_Price must be a number. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-320 | Story | NNB-205 | FV_UP77_Admin_If the new Price of the package is less than 0, the system will show the error. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-321 | Story | NNB-205 | FV_UP78_Admin_If the new Amount Post of the package is less than 0, the system will show the error. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-327 | Story | NNB-205 | FV_UP79_Admin_If the new Description of the package is blank, the system will show the error. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-328 | Story | NNB-205 | FV_UP80_Admin_If the new Package Name is blank, the system will show the error. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-330 | Story | NNB-205 | FV_UP81_Admin_If the new Package Name, Price, Amount Post, and Description are valid, the admin can update a new package. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-206 | Epic |  | View User Profile | To Do | Nguyen Huu Minh Tai (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-498 | Story | NNB-206 | FV_VUP15_Creator_Creator can view his profile by clicking on “Hello”. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-499 | Story | NNB-206 | FV_VUP16_Customer_Customer can view his profile by clicking on “Hello”. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-207 | Epic |  | Edit User Profile | To Do | Nguyen Huu Minh Tai (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-289 | Story | NNB-207 | TR_EUP11_Verify Phone Number_Phone Number must start with the digit 0 and have exactly 10 digits | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-292 | Story | NNB-207 | TR_EUP12_Verify Full Name_Full Name is required | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-357 | Story | NNB-207 | TR_EUP13_Verify Full Name_Full Name cannot contain numbers | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-358 | Story | NNB-207 | TR_EUP14_Verify Avatar Image_Avatar Image must be a jpg file | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-486 | Story | NNB-207 | FV_EUP17_Customer_Customer can edit his profile if all inputs are valid. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-487 | Story | NNB-207 | FV_EUP17.1_Customer_Customer can not edit his profile if once or all inputs are not valid. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-488 | Story | NNB-207 | FV_EUP18_Customer_If the phone number does not start with the digit 0 and has exactly 10 digits, show an error. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-489 | Story | NNB-207 | FV_EUP19_Customer_If the full name is null, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-490 | Story | NNB-207 | FV_EUP21_Customer_If the full name contains the number, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-491 | Story | NNB-207 | FV_EUP22_Customer_If the avatar image is not a jpg file, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-492 | Story | NNB-207 | FV_EUP22_Creator_Creator can edit his profile if all inputs are valid. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-493 | Story | NNB-207 | FV_EUP22.1_Creator_Creator can not edit his profile if once or all inputs are not valid. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-494 | Story | NNB-207 | FV_EUP23_Creator_If the phone number does not start with the digit 0 and has exactly 10 digits, show an error. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-495 | Story | NNB-207 | FV_EUP24_Creator_If the full name is null, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-496 | Story | NNB-207 | FV_EUP25_Creator_If the full name contains the number, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-497 | Story | NNB-207 | FV_EUP26_Creator_If the avatar image is not a jpg file, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-208 | Epic |  | Change Password | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-537 | Story | NNB-208 | TR_CP21_Verify password – Password is quired. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-540 | Story | NNB-208 | TR_CP22_Verify password – Password must be at least 6 and at max 100 characters long. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-541 | Story | NNB-208 | TR_CP23_Verify password – Password must have at least one non alphanumeric character. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-542 | Story | NNB-208 | TR_CP24_Verify password - Password must have at least one lowercase character. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-543 | Story | NNB-208 | TR_CP25_Verify password - Password must have at least one upper character. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-209 | Epic |  | Reset Password | To Do | Nguyen Huu Minh Tai (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-387 | Story | NNB-209 | TR_RP15_Verify Password_Password is quired | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-388 | Story | NNB-209 | TR_RP16_Verify Password_Password must be at least 6 and at max 100 characters long | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-389 | Story | NNB-209 | TR_RP17_Verify Password_Password must have at least one non alphanumeric character | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-392 | Story | NNB-209 | TR_RP18_Verify Password_Password must have at least one lowercase character | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-393 | Story | NNB-209 | TR_RP19_Verify Password_Password must have at least one upper character | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-394 | Story | NNB-209 | TR_RP20_Verify Confirm Password_Confirm Password and Password must be the same | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-517 | Story | NNB-209 | FV_RP49_Customer/Creator_If the email is invalid, the system shows an error. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-518 | Story | NNB-209 | FV_RP50_Customer/Creator_If the email does not exist, the system shows an error. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-520 | Story | NNB-209 | FV_RP52_Customer/Creator_Send mail with callbackUrl if the email is valid. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-535 | Story | NNB-209 | FV_RP53_Customer/Creator_The callbackUrl is valid. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-528 | Story | NNB-209 | FV_RP60_Customer/Creator_If the password is null, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-529 | Story | NNB-209 | FV_RP61_Customer/Creator_If the password is less than 6 or more than 100 characters, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-530 | Story | NNB-209 | FV_RP62_Customer/Creator_If the password does not have any non-alphanumeric characters, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-531 | Story | NNB-209 | FV_RP63_Customer/Creator_If the password does not have any lowercase characters, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-532 | Story | NNB-209 | FV_RP64_Customer/Creator_If the password does not have any upper character, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-533 | Story | NNB-209 | FV_RP65_Customer/Creator_If the confirmation password is not the same as the new password, the system will show an error. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-534 | Story | NNB-209 | FV_RP66_Customer/Creator_If the confirmation password is the same as the new valid password, the customer can reset the password. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-210 | Epic |  | View Cart | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-269 | Story | NNB-210 | FV_VC68_Customer_Customer can view the list of artwork in carts of himself | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-277 | Story | NNB-210 | FV_VC69_Creator_Creator can view the list of artwork in carts of himself | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-461 | Story | NNB-210 | FV_VA104_Customer_The customer should view the artwork is not bought successfully. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-211 | Epic |  | Remove Item | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-281 | Story | NNB-211 | FV_RI74_Creator_Creators successfully removed the items | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-287 | Story | NNB-211 | FV_RI75_Customer_Customer successfully removed the items. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-212 | Epic |  | Place Order | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-238 | Story | NNB-212 | TR_PO49_Verify Name_Name is required | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-255 | Story | NNB-212 | TR_PO50_Verify Name_Name cannot contain numbers. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-261 | Story | NNB-212 | TR_PO51_Verify Phone Number_Phone Number is required. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-262 | Story | NNB-212 | TR_PO52_Verify Phone Number_The phone Number must start with the digit 0 and have exactly 10 digits | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-313 | Story | NNB-212 | FV_PO82_Customer_If the Name of the customer is blank, the system will show the error | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-323 | Story | NNB-212 | FV_PO83_Customer_If the phone number of the customer is blank, the system will show the error | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-326 | Story | NNB-212 | FV_PO84_Customer_If the phone number is not enough 10 digits, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-331 | Story | NNB-212 | FV_PO85_Customer_If the phone number does not begin with “0”, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-332 | Story | NNB-212 | FV_PO86_Customer_If the name and phone number are valid, the customer will place the order successfully. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-339 | Story | NNB-212 | FV_PO87_Creator_If the Name of the customer is blank, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-356 | Story | NNB-212 | FV_PO87.1_Creator_ If the Name of the customer contains the number, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-360 | Story | NNB-212 | FV_PO88_Creator_If the phone number of the customer is blank, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-376 | Story | NNB-212 | FV_PO89_Creator_If the phone number is not enough 10 digits, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-379 | Story | NNB-212 | FV_PO90_Creator_If the phone number does not begin with “0”, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-382 | Story | NNB-212 | FV_PO91_Creator_If the name and phone number are valid, the creator will place the order successfully. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-459 | Story | NNB-212 | FV_BO82.1_Customer_If the Name of the customer contains the number, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-213 | Epic |  | Pay By Stripe | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-396 | Story | NNB-213 | FV_PS92_Customer_If the email of the customer is blank, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-436 | Story | NNB-213 | FV_PS93_Customer_If the email of the customer is not valid, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-437 | Story | NNB-213 | FV_PS94_Customer_If the Card information of the customer is blank, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-439 | Story | NNB-213 | FV_PS95_Customer_If the Card information of the customer is not valid, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-442 | Story | NNB-213 | FV_PS95.1_Customer_If the Cardholder name of the customer is blank, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-443 | Story | NNB-213 | FV_PS96_Customer_If the Email, Card information, and Cardholder Name are valid, the customer will pay by Stripe successfully | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-444 | Story | NNB-213 | FV_PS97_Creator_If the email of the creator is blank, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-447 | Story | NNB-213 | FV_PS98_Creator_If the email of the creator is not valid, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-448 | Story | NNB-213 | FV_PS99_Creator_If the Card information of the creator is blank, the system will show the error | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-450 | Story | NNB-213 | FV_PS100_Creator_If the Card information of the creator is not valid, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-452 | Story | NNB-213 | FV_PS101_Creator_If the Cardholder name of the creator is blank, the system will show the error. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-454 | Story | NNB-213 | FV_PS102_Creator_If the Email, Card information, and Cardholder Name are valid, the creator will pay by Stripe successfully. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-214 | Epic |  | View Artworks | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-460 | Story | NNB-214 | FV_VA103_Customer_If the artwork is bought, the customer cannot see it on the home page | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-462 | Story | NNB-214 | FV_VA104_Customer_The customer should view the artwork is not bought successfully. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-463 | Story | NNB-214 | FV_VA105_Customer_If the artwork has been hidden by the moderator since reported, the customer cannot see it on the home page. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-464 | Story | NNB-214 | FV_VA105.1_Creator_If the artwork is bought, the creator cannot see it on the home page | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-465 | Story | NNB-214 | FV_VA106_Creator_The creator should view the artwork that is not bought successfully. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-466 | Story | NNB-214 | FV_VA107_Creator_If the artwork has been hidden by the moderator since reported, the creator cannot see it on the home page. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-467 | Story | NNB-214 | FV_VA108_Moderator_If the artwork is bought, the moderator cannot see it on the home page. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-468 | Story | NNB-214 | FV_VA109_Morderator_The moderator should view the artwork is not bought successfully. | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-469 | Story | NNB-214 | FV_VA110_Morderator_If the artwork has been hidden by the moderator, the moderator cannot see it on the home page | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-215 | Epic |  | View Artwork Detail | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-470 | Story | NNB-215 | FV_VAD111_Customer_If the artwork is bought, the customer cannot view the details of it | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-471 | Story | NNB-215 | FV_VAD115_Creator_If the artwork is bought, the creator cannot view the details of it | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-472 | Story | NNB-215 | FV_VAD118_Moderator_The moderator can view the artwork detail of an artwork | Done | Nguyen Tan Hung - K17 FPTU | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-216 | Epic |  | Add To Cart | To Do | Pham Le Quy Anh (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-333 | Story | NNB-216 | FV_ATC120_Customer_Customer successfully adds an artwork to the cart, the artwork must be in the cart. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-335 | Story | NNB-216 | FV_ATC121_Creator_Creator succesfully add an artwork to cart, artwork must be in the cart. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-217 | Epic |  | Report Artwork | To Do | Pham Le Quy Anh (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-337 | Story | NNB-217 | FV_RART122_Customer_Customer successfully report an artwork, artwork must be added to ReportArtwork table. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-338 | Story | NNB-217 | FV_RART123_Creator_Creator successfully report an artwork, artwork must be added to ReportArtwork table. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-340 | Story | NNB-217 | FV_RART124_Creator_Creator cannot report his artwork. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-218 | Epic |  | Search Artworks | To Do | Dang Cong Hung (K17 HCM) |  | 2024-03-14 | 2024-03-14 | 2024-03-31 | 2024-03-31 | purple
NNB-341 | Story | NNB-218 | FV_SA125_Customer_Customer successfully search artworks by keywords. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-343 | Story | NNB-218 | FV_SA126_Creator_Creator successfully search artworks by keywords. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-346 | Story | NNB-218 | FV_SA127_Moderator_Moderator successfully search artworks by keywords. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-219 | Epic |  | View Blogs | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-354 | Story | NNB-219 | FV_VB128_Customer_Customer successfully view all blogs on Blog Page. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-355 | Story | NNB-219 | FV_VB129_Creator_Creator successfully view all blogs on Blog Page. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-362 | Story | NNB-219 | FV_VB130_Moderator_Moderator successfully view all blogs on Blog Page. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-220 | Epic |  | View Blog Detail | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-370 | Story | NNB-220 | FV_VBD131_Customer_Customer successfully view a blog in detail on Blog Page. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-374 | Story | NNB-220 | FV_VBD132_Creator_Creator successfully view a blog in detail on Blog Page. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-375 | Story | NNB-220 | FV_VBD133_Moderator_Moderator successfully view a blog in detail on Blog Page. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-221 | Epic |  | Report Blog | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-377 | Story | NNB-221 | FV_RB134_Customer_Customer successfully report an blog, blog must be added to ReportBlog table. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-378 | Story | NNB-221 | FV_RB135_Creator_Creator successfully report an artwork, artwork must be added to ReportArtwork table. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-380 | Story | NNB-221 | FV_RB136_Creator_Creator cannot report his blog. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-222 | Epic |  | View Creator Profile | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-381 | Story | NNB-222 | FV_VCP137_Customer_Customer successfully view creator profile on Creator Profile Page. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-384 | Story | NNB-222 | FV_VCP138_Creator_Creator successfully view different creator profile on Creator Profile Page. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-385 | Story | NNB-222 | FV_VCP139_Moderator_Moderator successfully view creator profile on Creator Profile Page. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-223 | Epic |  | Report Creator | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-386 | Story | NNB-223 | FV_RC140_Customer_Customer successfully report a creator, reported creator must be added to ReportCreator table. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-390 | Story | NNB-223 | FV_RC141_Creator_Creator successfully report a different creator, reported creator must be added to ReportCreator table. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-395 | Story | NNB-223 | FV_RC142_Creator_Creator cannot report himself. | Done | Pham Le Quy Anh (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-224 | Epic |  | View List Order | To Do | Nguyen Huu Minh Tai (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-500 | Story | NNB-224 | FV_VLO143_Admin_Admin successfully view all orders. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-501 | Story | NNB-224 | FV_VLO144_Customer_Customer successfully view his own orders. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-502 | Story | NNB-224 | FV_VLO145_Creator_Creator successfully view his own orders. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-225 | Epic |  | View Order Detail | To Do | Nguyen Huu Minh Tai (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-503 | Story | NNB-225 | FV_VOD146_Admin_Admin successfully view an order in detail. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-504 | Story | NNB-225 | FV_VOD147_Customer_Customer successfully view an order in detail. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-505 | Story | NNB-225 | FV_VOD148_Creator_Creator successfully view an order in detail. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-226 | Epic |  | View Package | To Do | Nguyen Huu Minh Tai (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-506 | Story | NNB-226 | FV_VP149_Creator successfully view packages on the Package Page. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-227 | Epic |  | Process Order | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-263 | Story | NNB-227 | FV_PO150_Admin_Admin processes an order, the order status changes to “Processing”. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-228 | Epic |  | Complete Order | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-265 | Story | NNB-228 | FV_CO151_Admin_If an order is completed, the order status changes to “Completed”. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-229 | Epic |  | Cancel Order | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-267 | Story | NNB-229 | FV_CO152_Admin_If the order status is approved, cancel order will refund money, change the status to “Cancel”. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-268 | Story | NNB-229 | FV_CO153_Admin_If the order status is pending, change the status to “Cancel”. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-274 | Story | NNB-229 | FV_CO154_Customer_If the order status is pending, change the status to “Cancel”. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-276 | Story | NNB-229 | FV_CO155_Creator＿If the order status is pending, change the status to “Cancel”. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-230 | Epic |  | View List Blog | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-244 | Story | NNB-230 | FV_VLB156_[Admin]_ Admin successfully view all blogs on Blog List Page. | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-245 | Story | NNB-230 | FV_VLB157_[Admin]_Creator successfully view his own blogs on Blog List Page | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-231 | Epic |  | Create Blog | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-264 | Story | NNB-231 | FV_CB70_[Creator]_If the title is null, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-266 | Story | NNB-231 | FV_CB71_[Creator]_If the description is null, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-270 | Story | NNB-231 | FV_CB72_[Creator]_If the description is less than 100 characters, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-271 | Story | NNB-231 | FV_CB73_[Creator]_If an image is null, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-272 | Story | NNB-231 | FV_CB74_[Creator]_If an image is not a jpg file, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-273 | Story | NNB-231 | FV_CB06_[Creator]_Creator successfully create a blog | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-232 | Epic |  | Remove Blog | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-322 | Story | NNB-232 | FV_RB170_[Admin]_Admin successfully remove a blog on the Blog List Page | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-324 | Story | NNB-232 | FV_RB171_[Creator]_Creator successfully remove a blog on the Blog List Page | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-325 | Story | NNB-232 | FV_RB172_[Moderator]_Moderator successfully remove a blog on the Blog List Page | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-233 | Epic |  | Edit Blog | To Do | Dang Cong Hung (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-342 | Story | NNB-233 | FV_EB75_[Creator]_If the title is null, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-345 | Story | NNB-233 | FV_EB76_[Creator]_If the description is null, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-350 | Story | NNB-233 | FV_EB77_[Creator]_If the description is less than 100 characters, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-352 | Story | NNB-233 | FV_EB78_[Creator]_If an image is not a jpg file, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-353 | Story | NNB-233 | FV_EB79_[Creator]_Creator successfully edit a blog | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-278 | Epic |  | Upload Artwork | To Do | Tran Van Nhat (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-399 | Story | NNB-278 | TR_UA53_Verify Title_Title is required | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-400 | Story | NNB-278 | TR_UA54_Verify Title_Title can only contain letters and numbers, and must contain at least one letter | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-401 | Story | NNB-278 | TR_UA55_Verify Description_Description is required | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-402 | Story | NNB-278 | TR_UA56_Verify Description_Description must be at least 70 characters | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-403 | Story | NNB-278 | TR_UA57_Verify Price_Price is required | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-404 | Story | NNB-278 | TR_UA58_Verify Price_Price must be a valid number | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-405 | Story | NNB-278 | TR_UA59_Verify Price_Price must be greater than 0 | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-406 | Story | NNB-278 | TR_UA60_Verify Image_Image is required | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-407 | Story | NNB-278 | TR_UA61_Verify Image_Image must be a jpg file | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-507 | Story | NNB-278 | FV_UA175_Creator_If the title is null, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-508 | Story | NNB-278 | FV_UA176_Creator_If the title does not contain a letterm show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-509 | Story | NNB-278 | FV_UA177_Creator_If the description is null, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-510 | Story | NNB-278 | FV_UA178_Creator_If the description is less than 70 characters, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-511 | Story | NNB-278 | FV_UA179_Creator_If the price is less than 1, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-512 | Story | NNB-278 | FV_UA180_Creator_If the price is not a number, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-513 | Story | NNB-278 | FV_UA181_Creator_If the price is null, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-514 | Story | NNB-278 | FV_UA182_Creator_If an image is null, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-515 | Story | NNB-278 | FV_UA183_Creator_If an image is not a jpg file, show an error message. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-516 | Story | NNB-278 | FV_UA184_Creator_Creator successfully upload an artwork. | Done | Nguyen Huu Minh Tai (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-279 | Epic |  | Edit Artwork | To Do | Tran Van Nhat (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-282 | Story | NNB-279 | TR_EA62_Verify Title_Title is required. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-283 | Story | NNB-279 | TR_EA63_Verify Title_Title can only contain letters and numbers, and must contain at least one letter. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-284 | Story | NNB-279 | TR_EA64_Verify Description_Description is required. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-286 | Story | NNB-279 | TR_EA65_Verify Description_Description must be at least 70 characters. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-288 | Story | NNB-279 | TR_EA66_Verify Price_Price is required. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-290 | Story | NNB-279 | TR_EA67_Verify Price_Price must be a valid number | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-291 | Story | NNB-279 | TR_EA68_Verify Price_Price must be greater than 0. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-293 | Story | NNB-279 | TR_EA69_Verify Image_Image must be a jpg file. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-296 | Story | NNB-279 | FV_EA185_Creator_If the title is null, show an error message. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-298 | Story | NNB-279 | FV_EA186_Creator_If the title does not contain a letter show an error message. | Done | Dang Cong Hung (K17 HCM) | [5 empty] | purple
NNB-300 | Story | NNB-279 | FV_EA187_Creator_If the description is null, show an error message. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-301 | Story | NNB-279 | FV_EA188_Creator_If the description is less than 70 characters, show an error message. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-302 | Story | NNB-279 | FV_EA189_Creator_If the price is less than 1, show an error message. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-304 | Story | NNB-279 | FV_EA190_Creator_If the price is not a number, show an error message. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-305 | Story | NNB-279 | FV_EA191_Creator_If the price is null, show an error message. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-307 | Story | NNB-279 | FV_EA193_Creator_If an image is not a jpg file, show an error message. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-308 | Story | NNB-279 | FV_EA194_Creator_Creator successfully edit an artwork. | Done | Dang Cong Hung (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-391 | Epic |  | View List Artworks | To Do | Tran Van Nhat (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-397 | Story | NNB-391 | FV_VLA173_[Admin]_Admin successfully view all artworks on the Artwork List Page | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-398 | Story | NNB-391 | FV_VLA174_[Creator]_Creator successfully view his own artworks on the Artwork List Page | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-411 | Epic |  | Register Account | To Do | Tran Van Nhat (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-412 | Story | NNB-411 | FV_RA204_[Customer]_If the full name is null, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-413 | Story | NNB-411 | FV_RA205_[Customer]_If the full name contains number, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-438 | Story | NNB-411 | FV_RA206_[Customer]_If the email is null, show an error message. | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-440 | Story | NNB-411 | FV_RA207_[Customer]_If the email is invalid, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-441 | Story | NNB-411 | FV_RA208_[Customer]_If the password is null, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-417 | Story | NNB-411 | FV_RA209_[Customer]_If the password less than 6 or more than 100 characters, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-419 | Story | NNB-411 | FV_RA210_[Customer]_If the password does not have any non alphanumeric characters, show an error message. | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-421 | Story | NNB-411 | FV_RA211_[Customer]_If the password does not have any lowercase character, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-422 | Story | NNB-411 | FV_RA212_[Customer]_If the password does not have any upper character, show an error message. | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-424 | Story | NNB-411 | FV_RA213_[Customer]_If the confirmed password is not identical to the password, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-425 | Story | NNB-411 | FV_RA214_[Customer]_Customer successfully registered an account. | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-434 | Story | NNB-411 | FV_RA204_[Creator]_If the full name is null, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-435 | Story | NNB-411 | FV_RA205_[Creator]_If the full name contains number, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-445 | Story | NNB-411 | FV_RA206_[Creator]_If the email is null, show an error message. | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-446 | Story | NNB-411 | FV_RA207_[Creator]_If the email is invalid, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-449 | Story | NNB-411 | FV_RA208_[Creator]_If the password is null, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-451 | Story | NNB-411 | FV_RA209_[Creator]_If the password less than 6 or more than 100 characters, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-453 | Story | NNB-411 | FV_RA210_[Creator]_If the password does not have any non alphanumeric characters, show an error message. | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-455 | Story | NNB-411 | FV_RA211_[Creator]_If the password does not have any lowercase character, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-456 | Story | NNB-411 | FV_RA212_[Creator]_If the password does not have any upper character, show an error message. | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-457 | Story | NNB-411 | FV_RA213_[Creator]_If the confirmed password is not identical to the password, show an error message | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-458 | Story | NNB-411 | FV_RA215_[Creator]_Customer successfully registered an account. | Done | hoangtnse170464 | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-479 | Epic |  | Remove Artwork | To Do | Tran Van Nhat (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-476 | Story | NNB-479 | FV_RA196_Admin_Admin successfully remove an artwork. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-478 | Story | NNB-479 | TR_RA04_Creator successfully remove an artwork. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-481 | Epic |  | View List Reported Artwork | To Do | Tran Van Nhat (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-480 | Story | NNB-481 | TR_VLRA01_Moderator successfully view all reported artworks on the Reported Artwork List Page. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-538 | Epic |  | Hide Artwork | To Do | Tran Van Nhat (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-482 | Story | NNB-538 | TR_HA01_If the artwork is reported, moderator can hide the artwork, the button changes to “Hidden”. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-539 | Epic |  | Unhide Artwork | To Do | Tran Van Nhat (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-483 | Story | NNB-539 | TR_UA01_If the artwork is hidden, moderator can unhide the artwork, the button changes to “Unhidden”. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-544 | Epic |  | View List Reported Blog | To Do | Tran Van Nhat (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-484 | Story | NNB-544 | TR_VLRB01_Moderator successfully view all reported artworks on the Reported Blog List Page. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-545 | Epic |  | View List Reported Creator | To Do | Tran Van Nhat (K17 HCM) |  |  | 2024-03-14 |  | 2024-03-31 | purple
NNB-485 | Story | NNB-545 | TR_VLRC01_Moderator successfully view all reported creators on the Reported Creator List Page. | Done | Tran Van Nhat (K17 HCM) | NNB Sprint 5 |  | 2024-03-14 |  | 2024-03-31 | purple

## Cover
TEST REPORT DOCUMENT
Project Name | Banking Project |  |  | Creator | Chi Le
Project Code | BP |  |  | Issue Date | 2024-01-11
Document Code | BP |  |  | Version
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
Note on D10: ====== ID#AAAA4IanTyo (2023-09-09 06:57:24) *A: Add M: Modify D: Delete

## Edit Customer
Feature | Edit Customer | [13 empty] | Passed
Test requirement | Mobile application and Web browser of Edit Customer | [13 empty] | Failed
Number of TCs | 21 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 5 | 2 | 0 | 0
Round 2 | 6 | 1 | 0 | 0
Round 3 | 6 | 1 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Login | Login
EC01 | Login sucessfully as a Admin Account | 1. Admin enter correct username and password in Login page 2. Press login button | Application redirect to admin home page and pop up message "Login successfully" | username: "foxmanager" password:"zaQ@1234" | Passed | 2023-09-25 | Tom | Passed | 2023-09-25 | Luke | Passed | 2023-09-25 | Handy
ED02 | Login fail as Admin Account | 1. Admin enter incorrect username and password in Login page 2. Press login button | Application pop up message "Wrong username or password" | username: "foxmanager" password:"zaQ@" | Passed | 2023-09-25 | Tom | Passed | 2023-09-25 | Luke | Passed | 2023-09-25 | Handy
ED03 | Login successfully as Customer by OTP | 1. Customer choose "Đăng nhập bằng mã OTP" button in Login page 2. Enter user phone number 3. Wait for OTP code to be sent via sms message 4. Enter OTP code and press confirm button | Application redirect to customer home page and pop up message "Login successfully" | isPhone: true, idToken: "", fcmToken: "" | Failed | 2023-09-25 | Tom | Passed | 2023-09-25 | Luke | Passed | 2023-09-25 | Handy | Round 1: Application do not redirect to home page
ED04 | Login successfully as Customer by email | 1. Customer choose "Đăng nhập bằng email" button in Login page 2. User enter email and password 3. Confirm email and password | Application redirect to customer home page and pop up message "Login successfully" | isPhone: true, idToken: "", fcmToken: "" | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Luke | Passed | 2023-09-26 | Handy
ED05 | Login successfully as Staff | 1. Staff enter username and password in Login page 2. Press login button | Application redirect to staff home page and pop up message "Login successfully" | username: "staff" password:"zaQ@1234" | Failed | 2023-09-26 | Tom | Failed | 2023-09-26 | Luke | Failed | 2023-09-26 | Handy | Round 1: Pop up "incorrect username or password"
ED06 | Login successfully as Shipper | 1. Shipper enter username and password in Login page 2. Press login button | Application redirect to shipper home page and pop up message "Login successfully" | username: "shipper" password:"zaQ@1234" | Passed | 2023-09-27 | Tom | Passed | 2023-09-27 | Luke | Passed | 2023-09-27 | Handy
Logout
ED07 | Logout from Customer | 1. Customer click to "Logout" button | Application redirect to login page | Have logged into a customer's account | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Luke | Passed | 2023-09-26 | Handy

## Test Cases
TEST CASE LIST
Project Name |  | Banking Project
Project Code |  | BP
Test Environment Setup Description |  | 1. API 2. Mobile application 3. Web Browser
No | Function Name | Sheet Name | Description | Pre-Condition
1 | New Customer | New Customer | Add new customer | New Customer (API)'
2 | Edit Customer | Edit Customer | Edit Customer | New Customer
3 | New Account | New Account | Add new account
4 | Edit Account | Edit Account | Edit Account | New Account

## Test Statistics
TEST STATISTICS
Project Name | Banking Project |  | Creator |  |  | Chi Le
Project Code | BP |  | Reviewer/Approver
Document Code | BP_Test Report |  | Issue Date |  |  | 2024-01-11
Notes
No | Module code | Passed | Failed | Pending | N/A | Number of test cases
1 | New Account | 13 | 8 | 0 | 0 | 21
2 | Edit New Account | 17 | 4 | 0 | 0 | 21
3 | New Customer | 49 | 44 | 0 | 0 | 93
4 | Edit New Customer | 50 | 22 | 0 | 0 | 72
| Sub total | 129 | 78 | 0 | 0 | 207
| Test coverage |  | 100 | %
| Test successful coverage |  | 62.3188 | %

## New Customer (API)
Feature | New Customer (API) | [13 empty] | Passed
Test requirement | API of Authentication and Authorization | [13 empty] | Failed
Number of TCs | 21 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 4 | 3 | 0 | 0
Round 2 | 4 | 3 | 0 | 0
Round 3 | 5 | 2 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Login | Login
ANA01 | Login sucessfully as a Admin Account | 1. Send a request login by JSON 2. Click button execute on Swagger | Status code is 200 - return JWT with correct information including the admin | username: "foxmanager" password:"zaQ@1234" | Passed | 2023-09-25 | Tom | Passed | 2023-09-25 | Jenni | Passed | 2023-09-25 | Luke
ANA02 | Login fail as Admin Account | 1. Send a request login by JSON 2. Click button execute on Swagger | Status code is 400 - return with error message | username: "foxmanager" password:"zaQ@" | Passed | 2023-09-25 | Tom | Passed | 2023-09-25 | Jenni | Passed | 2023-09-25 | Luke
ANA03 | Login successfully as Customer | 1. Send a request login by JSON 2. Click button execute on Swagger | Status code is 200 - return JWT with correct information including the customer | isPhone: true, idToken: "", fcmToken: "" | Failed | 2023-09-25 | Tom | Failed | 2023-09-25 | Jenni | Failed | 2023-09-25 | Luke | Login fail - status code is 400
ANA04 | Login successfully as Customer | 1. Send a request login by JSON 2. Click button execute on Swagger | Status code is 200 - return JWT with correct information including the customer | isPhone: true, idToken: "", fcmToken: "" | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
ANA05 | Login successfully as Staff | 1. Send a request login by JSON 2. Click button execute on Swagger | Status code is 200 - return JWT with correct information including the customer | username: "staffmanager" password:"zaQ@1234" | Failed | 2023-09-26 | Tom | Failed | 2023-09-26 | Jenni | Failed | 2023-09-26 | Luke | Login fail - status code is 400
ANA06 | Login successfully as Customer | 1. Send a request login by JSON 2. Click button execute on Swagger | Status code is 200 - return JWT with correct information including the customer | username: "staffmanager" password:"zaQ@1234" | Failed | 2023-09-27 | Tom | Failed | 2023-09-27 | Jenni | Passed | 2023-09-27 | Luke
Logout
ANA07 | Logout from Customer | 1. Send a request logout by JSON 2. Click button execute on Swagger | Status code is 200 - logout from the customer's account | Have logged into a customer's account | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Note on E10: ====== ID#AAAA4IanTyk tqsang (2023-09-09 06:57:24) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case